## فيلا تجريبية
Create professional Gantt charts in GanttPRO in a few clicks
فيلا تجريبية | [12 empty] | 2025-12-08 08:03
Color | WBS Number |  |  |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Predecessor | Budget | Actual cost | Created | Creator | Type | Project | Level
| 1 | أعمال الموقع | [5 empty] | 2025-11-02 07:00 | 2025-11-06 07:00 |  | 0 | 28 | [8 empty] | 2025-10-01 06:00 | Invented Creator | project | فيلا تجريبية | 1
| 1.1 |  | التجهيز |  |  |  |  | 2025-11-02 07:00 | 2025-11-06 07:00 |  | 0 | 28 | [8 empty] | 2025-10-01 06:00 | Invented Creator | tasks group | فيلا تجريبية / أعمال الموقع | 2
| 1.1.1 |  |  | تسوير الموقع |  |  | Sami Rahman | 2025-11-02 07:00 | 2025-11-02 16:00 |  | 100 | 8 | 8 | 480 | Done | High |  |  | 1200 | 1000 | 2025-10-01 06:00 | Invented Creator | task | فيلا تجريبية / أعمال الموقع / التجهيز | 3
| 1.1.2 |  |  | Site survey |  |  | noura.k | 2025-11-03 07:00 | 2025-11-03 11:00 |  | 50 | 4 | 4 | 60 | In progress | Medium |  | 1.1.1 |  |  | 2025-10-01 06:00 | Invented Creator | task | فيلا تجريبية / أعمال الموقع / التجهيز | 3
| 1.1.3 |  |  | الأساسات |  |  |  | 2025-11-04 07:00 | 2025-11-05 16:00 |  | 0 | 16 | [8 empty] | 2025-10-01 06:00 | Invented Creator | tasks group | فيلا تجريبية / أعمال الموقع / التجهيز | 3
| 1.1.3.1 |  |  |  | الحفر |  |  | 2025-11-04 07:00 | 2025-11-05 16:00 |  | 0 | 16 | [8 empty] | 2025-10-01 06:00 | Invented Creator | tasks group | فيلا تجريبية / أعمال الموقع / التجهيز / الأساسات | 4
| 1.1.3.1.1 |  |  |  |  | حفر القواعد | Unknown Person, Sami Rahman | 2025-11-04 07:00 | 2025-11-05 11:00 | 2025-11-06 23:58 | 0 | 12 | 0 | 0 | Open | Lowest |  | 1.1.2 |  |  | 2025-10-01 06:00 | Invented Creator | task | فيلا تجريبية / أعمال الموقع / التجهيز / الأساسات / الحفر | 5
| 1.1.3.1.2 |  |  |  |  | صب النظافة |  | 2025-11-05 12:00 | 2025-11-05 16:00 |  | 0 | 4 | 0 | 0 | Open | Medium |  | 1.1.3.1.1 | 300 |  | 2025-10-01 06:00 | Invented Creator | task | فيلا تجريبية / أعمال الموقع / التجهيز / الأساسات / الحفر | 5
| 1.1.4 |  |  | اعتماد التصميم |  |  |  | 2025-11-06 07:00 | 2025-11-06 07:00 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 1.1.3.1.2 |  |  | 2025-10-01 06:00 | Invented Creator | milestone | فيلا تجريبية / أعمال الموقع / التجهيز | 3
| 2 | Finishing | [5 empty] | 2025-11-09 07:00 | 2025-11-11 10:00 |  | 0 | 19 | [8 empty] | 2025-10-01 06:00 | Invented Creator | project | فيلا تجريبية | 1
| 2.1 |  | Painting |  |  |  | Sami Rahman | 2025-11-09 07:00 | 2025-11-10 16:00 |  | 25 | 16 | 0 | 0 | On hold | Highest |  |  |  | 50 | 2025-10-01 06:00 | Invented Creator | task | فيلا تجريبية / Finishing | 2
| 2.2 |  | Cleaning |  |  |  | noura.k | 2025-11-11 08:00 | 2025-11-11 10:00 |  | 0 | 2 | 0 | 0 | Weird | Low | See https://example.com/spec Second line | 2.1FS+1h |  |  | 2025-10-01 06:00 | Invented Creator | task | فيلا تجريبية / Finishing | 2
| 3 | Handover | [5 empty] | 2025-11-12 07:00 | 2025-11-12 08:00 |  | 0 | 1 | 0 | 0 | Closed | Medium |  | 2.2; 1.1.4 |  |  | 2025-10-01 06:00 | Invented Creator | task | فيلا تجريبية | 1
This document has been created with the help of https://ganttpro.com online service